## Sheet1
Phase | Task | Start Date | End Date | Duration | Type of Roadmap
Platform Roadmap: Phase 1 |  |  |  |  | Platform
| Create Admin and AskCal Apps | Day 1 | Day 30 | 30 days | Platform
| Develop data and model catalogs | Day 5 | Day 25 | 20 days | Platform
| Build apps marketplace | Day 10 | Day 30 | 20 days | Platform
| Enable AskCal per app question handling | Day 15 | Day 35 | 20 days | Platform
Platform Roadmap: Phase 2 |  |  |  |  | Platform
| Create Solutions tab in AskCal app | Day 36 | Day 56 | 20 days | Platform
| Add Solutions Request tab in Admin App | Day 40 | Day 60 | 20 days | Platform
| Implement feedback collection and refinement | Day 45 | Day 65 | 20 days | Platform
Platform Roadmap: Phase 3 |  |  |  |  | Platform
| Integrate Agenta ecosystem | Day 66 | Day 96 | 30 days | Platform
| New request capability for SMEs | Day 70 | Day 100 | 30 days | Platform
| Configure and launch agents via Admin | Day 75 | Day 105 | 30 days | Platform
AskCal Admin RoadMap: Phase 1 |  |  |  |  | Admin
| Data: Catalogue of datasets | Day 1 | Day 30 | 30 days | Admin
| Models: Catalogue of models | Day 5 | Day 35 | 30 days | Admin
| Apps: Marketplace for AskCal apps | Day 10 | Day 40 | 30 days | Admin
| Solutions: List solutions in each AskCal app | Day 15 | Day 45 | 30 days | Admin
| Settings: User management and access control | Day 20 | Day 50 | 30 days | Admin
AskCal Admin RoadMap: Phase 2 |  |  |  |  | Admin
| Enhance solution generation via Langflow | Day 51 | Day 81 | 30 days | Admin
| Improve Phase 1 features (data, model, apps) | Day 55 | Day 85 | 30 days | Admin
AskCal Admin RoadMap: Phase 3 |  |  |  |  | Admin
| Add capability to build agents dynamically | Day 86 | Day 116 | 30 days | Admin
| Enhance solution workflow and functions | Day 90 | Day 120 | 30 days | Admin
AskCal ISO RoadMap: Phase 1 |  |  |  |  | ISO
| Enable generic AskCal queries | Day 1 | Day 30 | 30 days | ISO
| Develop solution request form integration with ServiceNow | Day 5 | Day 35 | 30 days | ISO
| Implement SSO integration | Day 10 | Day 40 | 30 days | ISO
AskCal ISO RoadMap: Phase 2 |  |  |  |  | ISO
| Enable real-time solution requests | Day 41 | Day 71 | 30 days | ISO
| Manage solution access settings | Day 45 | Day 75 | 30 days | ISO
| Test and assign published solutions | Day 50 | Day 80 | 30 days | ISO
AskCal ISO RoadMap: Phase 3 |  |  |  |  | ISO
| Automate tasks via agents | Day 81 | Day 111 | 30 days | ISO
| Enhance SME prompt generation automation | Day 85 | Day 115 | 30 days | ISO